## Status
RQ 1: what are the influential sources of evidence? | Status | Responsible | Comments
1 Extraction of all references from guideline documents | D | MS
2 Tidying and coding to network matrix | D | MS/AB
3 Visualisation of data | D | MS/AB
4 Analysis and visualisation of most influential | D | MS/AB
5 Analysis of study design/conflicts of interest | D | MS/AB
RQ2: Do GL documents with similar conclusions cite the same sources?
1 Likert scale for strength/direction of recommendation | N | MS/SVK/SH
2 Coding of guideline documents | N | MS/AB
3 Block modelling – grouped by common citations, coloured by recommendation | N | MS/AB/MM
4 Visualisation of grouped network | N | MS/AB/MM
RQ3: Are CoIs changing over time?
1 Screen all referenced documents for published reports and articles | I | MS/AB | This is a manual process, to turn the text of the bibliographies of the GLs into full references through Shiny-managed Scopus search 496/2330 done
2 Get full text for all included | I | MS/AB
3 Extract CoI/funding sources from meta-data/article text | N | MS/AB
4 Code into CoI categories | N | MS/AB
5 Visualisation of change of CoI distribution over time | N | MS/AB

## Gantt chart
| 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01
RQ 1: what are the influential sources of evidence?
1 Extraction of all references from guideline documents | bar: 2019-09-01
2 Tidying and coding to network matrix | bar: 2019-09-01 to 2019-10-01
3 Visualisation of data | bar: 2019-10-01 to 2019-11-01
4 Analysis and visualisation of most influential | bar: 2019-10-01 to 2019-11-01
5 Analysis of study design/conflicts of interest | bar: 2019-10-01 to 2019-11-01
RQ2: Do GL documents with similar conclusions cite the same sources?
1 Likert scale for strength/direction of recommendation | bar: 2020-01-01
2 Coding of guideline documents | bar: 2020-02-01
3 Block modelling – grouped by common citations, coloured by recommendation | bar: 2020-01-01 to 2020-03-01
4 Visualisation of grouped network | bar: 2020-02-01 to 2020-03-01
RQ3: Are CoIs changing over time?
1 Screen all referenced documents for published reports and articles | bar: 2019-12-01 to 2020-02-01
2 Get full text for all included | bar: 2019-12-01 to 2020-03-01
3 Extract CoI/funding sources from meta-data/article text | bar: 2020-02-01 to 2020-04-01
4 Code into CoI categories | bar: 2020-02-01 to 2020-04-01
5 Visualisation of change of CoI distribution over time | bar: 2020-03-01 to 2020-04-01